## Exhibit 3
Blue Gilia Construction, Inc.
Percentage-of-Completion Schedule
December 31, 2017
| % Complete |  | Estimated | Actual | Estimated | Estimated |  |  | Actual
| (Based on | Expected | Total | To-Date | Total | To-Date | Construction | % | Progress | Billings on CIP | CIP in Excess of
Job | Costs) | Revenue | Costs | Costs | Profits | Profits | in Progress | Billed | Billings | in Excess of CIP | Billings on CIP
A | B | C | D | E | F | G | H | I | J | K | L
Formula | E/D |  |  |  | C-D | F*B | G+E | J/C |  | J-H | J-H
AEI-2101 | 25.35% | 72300 | 57000 | 14448 | 15300 | 3878 | 18326 | 32.78% | 23700 | 5374
ANA-0119 | 63.09% | 20400 | 16500 | 10410 | 3900 | 2461 | 12871 | 49.02% | 10000 |  | 2871
ARA-1801 | 46.03% | 32800 | 26500 | 12199 | 6300 | 2900 | 15099 | 54.88% | 18000 | 2901
AZU-2501 | 68.18% | 22400 | 18600 | 12682 | 3800 | 2591 | 15273 | 71.43% | 16000 | 727
BRO-1601 | 76.53% | 18500 | 14800 | 11326 | 3700 | 2832 | 14158 | 43.24% | 8000 |  | 6158
CAP-2020 | 14.02% | 10350 | 8500 | 1192 | 1850 | 259 | 1451 | 24.15% | 2500 | 1049
CAP-2005 | 54.93% | 46000 | 38000 | 20873 | 8000 | 4394 | 25267 | 52.17% | 24000 |  | 1267
CHA-2209 | 115.6% | 78000 | 45000 | 52000 | 33000 | 38133 | 90133 | 89.74% | 70000 |  | 20133
CHR-2201 | 9.291% | 92000 | 74000 | 6875 | 18000 | 1672 | 8547 | 10.33% | 9500 | 953
CIT-0202 | 53.84% | 10000 | 8900 | 4792 | 1100 | 592 | 5384 | 40% | 4000 |  | 1384
COC-2201 | 71.66% | 11300 | 9350 | 6700 | 1950 | 1397 | 8097 | 44.25% | 5000 |  | 3097
CRO-1801 | 23.34% | 91800 | 75200 | 17553 | 16600 | 3875 | 21428 | 19.61% | 18000 |  | 3428
ENE-1701 | 63.12% | 11250 | 9350 | 5902 | 1900 | 1199 | 7101 | 64% | 7200 | 99
ENE-3503 | 6.963% | 46500 | 38200 | 2660 | 8300 | 578 | 3238 | 7.527% | 3500 | 262
FIT-0401 | 58.32% | 8000 | 6800 | 3966 | 1200 | 700 | 4666 | 37.5% | 3000 |  | 1666
GEC-1801 | 75.2% | 45600 | 37500 | 28199 | 8100 | 6091 | 34290 | 83.33% | 38000 | 3710
GLO-2501 | 12.25% | 177200 | 145000 | 17762 | 32200 | 3944 | 21706 | 14.67% | 26000 | 4294
LOC-0116 | 78.26% | 9400 | 7520 | 5885 | 1880 | 1471 | 7356 | 53.19% | 5000 |  | 2356
MOR-0301 | 69.99% | 18500 | 15500 | 10849 | 3000 | 2100 | 12949 | 86.49% | 16000 | 3051
NOR-1924 | 70.38% | 9100 | 7100 | 4997 | 2000 | 1408 | 6405 | 42.59% | 3876 |  | 2529
NOR-5627 | 44.88% | 16000 | 15200 | 6822 | 800 | 359 | 7181 | 53.12% | 8500 | 1319
RET-2501 | 51.05% | 95500 | 76500 | 39056 | 19000 | 9700 | 48756 | 41.88% | 40000 |  | 8756
STI-0101 | 61.54% | 15800 | 12700 | 7816 | 3100 | 1908 | 9724 | 50% | 7900 |  | 1824
USO-3201 | 74.79% | 42300 | 33850 | 25316 | 8450 | 6320 | 31636 | 77.54% | 32800 | 1164
VIS-3302 | 63.4% | 56000 | 45000 | 28531 | 11000 | 6974 | 35505 | 65.44% | 36649 | 1144
WES-2401 | 49.28% | 47000 | 37600 | 18528 | 9400 | 4632 | 23160 | 38.3% | 18000 |  | 5160
| 42.87% | 1104000 | 880170 | 377339 | 223830 | 112368 | 489707 | 41.23% | 455125 | 26047 | 60629
34582